## Overview
RRM-1 — Project Tracker
Robotics Reasoning Model · github.com/o-abolade/rrm
Anchor deadline | IROS 2027 — 1 March 2027
Project start | 2026-08-16
Days to submission | 197
ICRA 2027 main track | 15 September 2026 — not a target; workshop outlet at best
CoRL 2027 | ~April 2027 — secondary
Benchmark tasks | 5 of 10 implemented
Metrics instrumented | 10 of 45
Hardware | A10G · 22.35 GiB usable VRAM · 8 vCPU · 32 GiB RAM
Tabs | Schedule · Gates · Metrics · Baselines · Weights
Regenerate with: python3 scripts/make_tracker.py
Source of truth is docs/roadmap.md and docs/evaluation_matrix.md — edit those, then regenerate.

## Schedule
Workstream | Task | Start | End | Days | Offset | Kind | Status | % Done | Notes
W1 Isaac backend | Provision instance, verify environment | 2026-08-16 | 2026-08-20 | 4 | 0 | Build | Not started | 0%
W1 Isaac backend | USD scene — Panda, table, cup, annotations | 2026-08-20 | 2026-08-31 | 11 | 4 | Build | Not started | 0%
W1 Isaac backend | Deterministic episode reset | 2026-08-31 | 2026-09-09 | 9 | 15 | Gate | Not started | 0%
W1 Isaac backend | observe() — poses, relation inference | 2026-09-05 | 2026-09-14 | 9 | 20 | Build | Not started | 0%
W1 Isaac backend | apply() — trajectory publish, sim step | 2026-09-12 | 2026-09-20 | 8 | 27 | Build | Not started | 0%
W2 GR00T policy | Load N1.7-3B, LIBERO_PANDA embodiment | 2026-09-21 | 2026-09-25 | 4 | 36 | Build | Not started | 0%
W2 GR00T policy | EmbodimentAdapter — verb to instruction + pose | 2026-09-26 | 2026-10-02 | 6 | 41 | Build | Not started | 0%
W2 GR00T policy | Observation dict, chunk to JointTrajectory | 2026-10-03 | 2026-10-10 | 7 | 48 | Build | Not started | 0%
W2 GR00T policy | Numeric safety — URDF limits, swept volume | 2026-10-08 | 2026-10-18 | 10 | 53 | Gate | Not started | 0%
W3 Learned reasoner | vLLM serving, guided_json smoke test | 2026-10-19 | 2026-10-21 | 2 | 64 | Build | Not started | 0%
W3 Learned reasoner | Prompt generated from VERB_TABLE, versioned | 2026-10-22 | 2026-10-27 | 5 | 67 | Build | Not started | 0%
W3 Learned reasoner | LocalReasoner — parser, validator, repair | 2026-10-28 | 2026-11-03 | 6 | 73 | Build | Not started | 0%
W3 Learned reasoner | Oracle vs learned reasoner comparison | 2026-11-04 | 2026-11-08 | 4 | 80 | Build | Not started | 0%
W4 Tasks and metrics | T3, T4, T7 — long-horizon and dynamic scenes | 2026-11-09 | 2026-11-20 | 11 | 85 | Build | Not started | 0%
W4 Tasks and metrics | T5 ambiguity, T10 held-out layouts | 2026-11-21 | 2026-11-28 | 7 | 97 | Build | Not started | 0%
W4 Tasks and metrics | Safety-labelled scenarios | 2026-11-23 | 2026-12-02 | 9 | 99 | Gate | Not started | 0%
W4 Tasks and metrics | Close metric instrumentation gaps | 2026-11-30 | 2026-12-06 | 6 | 106 | Build | Not started | 0%
W5 Baseline arms | Baseline A — VLA direct from mission | 2026-12-07 | 2026-12-13 | 6 | 113 | Build | Not started | 0%
W5 Baseline arms | Baseline B — reasoner, no world model | 2026-12-14 | 2026-12-20 | 6 | 120 | Build | Not started | 0%
W5 Baseline arms | Baseline C — world model, no predictive layer | 2026-12-21 | 2026-12-27 | 6 | 127 | Slack | Not started | 0%
W5 Baseline arms | Arm-switching harness | 2026-12-28 | 2027-01-03 | 6 | 134 | Build | Not started | 0%
W6 Benchmark | Seeded sweeps — N episodes x task x arm | 2027-01-04 | 2027-01-17 | 13 | 141 | Build | Not started | 0%
W6 Benchmark | Ablations — world model, predictive, safety | 2027-01-18 | 2027-01-24 | 6 | 155 | Build | Not started | 0%
W6 Benchmark | Analysis, results frozen | 2027-01-25 | 2027-01-31 | 6 | 162 | Build | Not started | 0%
W7 Paper | Draft | 2027-02-01 | 2027-02-14 | 13 | 169 | Write | Not started | 0%
W7 Paper | Figures generated from traces | 2027-02-08 | 2027-02-18 | 10 | 176 | Write | Not started | 0%
W7 Paper | Review and revision | 2027-02-15 | 2027-02-25 | 10 | 183 | Write | Not started | 0%
W7 Paper | IROS 2027 submission | 2027-02-25 | 2027-03-01 | 4 | 193 | Gate | Not started | 0%
Offset = days from project start; pair with Days to build a stacked-bar Gantt.
Gate = slippage reaches the submission date instead of being absorbed. See Gates tab.

## Gates
Start | End | Gate | Stream | Why it blocks | Status | Risk notes
2026-08-31 | 2026-09-09 | Deterministic episode reset | W1 | Isaac physics is not reproducible by default and every reported number needs seeded episodes. Nothing in W4-W6 is publishable without it, which is why it precedes observe() despite being the less interesting task. | Not started
2026-10-08 | 2026-10-18 | Swept-volume collision checking | W2 | Safety #2 checks scalars against placeholder ranges today: structurally correct, numerically fake. Collision rate and safety violation rate are both meaningless until it is real. Most likely item to be underestimated. | Not started
2026-11-23 | 2026-12-02 | Safety-labelled scenarios | W4 | Verifier precision, recall and false-negative rate cannot come from traces — traces record what the verifier decided, never whether it was right. Scenarios must carry known-unsafe actions labelled in advance. Retrofitting invalidates every episode collected before the change. | Not started
2027-02-25 | 2027-03-01 | IROS 2027 submission | W7 | Four days of buffer is thin. Mitigation is freezing results on 31 January and refusing to re-run sweeps during write-up. | Not started

## Metrics
Category | Metric | Definition | Target | Source | Instrumentation group | Unblocked by | Current | Measured on | Notes
Task Success | Task Success Rate | Successful missions / total missions | >85% | task_success | Live now | -
Task Success | Partial Completion Rate | Missions partially completed / total | >90% | goal predicate subsets | New instrumentation | W4
Task Success | Goal Verification Accuracy | Correct identification of task completion | >90% | system must claim completion | New instrumentation | W4
Reasoning | Task Decomposition Accuracy | Correct subtasks / expected subtasks | >85% | diff vs Oracle task graph | Free from Oracle | W3
Reasoning | Step Ordering Accuracy | Correct ordering / total dependencies | >90% | diff vs Oracle ordering | Free from Oracle | W3
Reasoning | Spatial Reasoning Accuracy | Correct spatial relationships / tested | >90% | dedicated probe set | Needs ground truth | W4
Reasoning | Temporal Reasoning Accuracy | Correct temporal dependencies / tested | >90% | dedicated probe set | Needs ground truth | W4
World Model | Object-State Accuracy | Correct object states / total objects | >90% | WorldState vs USD stage | Unlocked by Isaac | W1
World Model | Spatial State Accuracy | Correct positions and relations | >90% | infer_relations vs stage | Unlocked by Isaac | W1
World Model | State Transition Accuracy | Correct state updates after actions | >90% | divergence records | Live now | -
World Model | Memory Consistency | Correct historical state retrieval | >90% | historical state queries | New instrumentation | W4
Planning | Plan Validity Rate | Executable plans / generated plans | >95% | validator accept / total | Free from Oracle | W3
Planning | Planning Time | Time to generate a valid plan | Minimize | planning_latency_ms | Live now | -
Planning | Action Efficiency | Required actions / executed actions | >85% | Oracle action_count as optimum | Free from Oracle | W3
Planning | Replanning Rate | Tasks requiring replanning / total | <20% | replans | Live now | -
Execution | Action Success Rate | Successful actions / attempted | >90% | dispatch termination | Live now | -
Execution | Manipulation Success | Successful grasps and placements / attempts | >90% | per-verb dispatch outcome | Unlocked by Isaac | W2
Execution | Navigation Success | Successful navigation tasks / attempts | >95% | per-verb dispatch outcome | Deferred | Phase 6
Execution | Execution Time | First action to completion | Minimize | simulator clock | Unlocked by Isaac | W1
Safety | Safety Violation Rate | Unsafe actions / total actions | ~0% | unsafe_actions / action_count | Live now | -
Safety | Collision Rate | Collisions / total trials | ~0% | Isaac contact reporting | Unlocked by Isaac | W2
Safety | Safety Verifier Recall | Unsafe actions correctly rejected | >99% | labelled unsafe actions | Needs ground truth | W4 GATE
Safety | Safety Verifier Precision | Rejected actions that were unsafe | >95% | labelled unsafe actions | Needs ground truth | W4 GATE
Safety | False-Negative Rate | Unsafe actions incorrectly permitted | <1% | labelled unsafe actions | Needs ground truth | W4 GATE
Recovery | Failure Detection Rate | Detected failures / injected failures | >90% | divergences / injected faults | New instrumentation | W4
Recovery | Recovery Success Rate | Recovered / detected failures | >80% | recoveries / divergences | Live now | -
Recovery | Recovery Time | Detection to successful recovery | Minimize | trace timestamps | New instrumentation | W4
Recovery | Recovery Action Overhead | Additional actions after failure | Minimize | action_count delta | New instrumentation | W4
Generalization | Environment Generalization | Performance on unseen environments | >75% retained | held-out scene library | Deferred | W4 partial
Generalization | Object Generalization | Performance on unseen objects | >75% retained | held-out object set | Deferred | W4 partial
Generalization | Instruction Generalization | Performance on novel phrasings | >80% retained | paraphrase set | Needs ground truth | W4
Generalization | Embodiment Transfer | Performance on unseen embodiment | >70% retained | UNITREE_G1 adapter swap | Deferred | Post-IROS
Robustness | Sensor Robustness | Performance under noise and dropout | >80% retained | real perception stack | Deferred | Phase 6
Robustness | Occlusion Robustness | Performance under partial occlusion | >80% retained | real perception stack | Deferred | Phase 6
Robustness | Dynamic Environment Robustness | Performance with moving obstacles | >80% retained | T6, T7 scenes | Unlocked by Isaac | W4
Robustness | Disturbance Recovery | Recovery after perturbation | >80% | T7 scenes | Unlocked by Isaac | W4
Sim-to-Real | Sim Success Rate | Success rate in simulation | >85% | task_success | Live now | -
Sim-to-Real | Real Success Rate | Success rate on physical robot | >75% | physical robot | Deferred | Post-IROS
Sim-to-Real | Sim-to-Real Gap | Simulation minus real performance | <15% | physical robot | Deferred | Post-IROS
Efficiency | Inference Latency | Model inference per reasoning cycle | Minimize | model call timing | New instrumentation | W3
Efficiency | GPU Memory | Peak GPU memory usage | Minimize | sampled during run | Unlocked by Isaac | W2
Efficiency | Compute Cost | Compute per completed task | Minimize | wall clock x instance rate | New instrumentation | W6
Efficiency | Token / Model Calls | AI calls required per task | Minimize | reasoner call counter | New instrumentation | W3
Long-Horizon | Success vs Task Horizon | Success as action count increases | >70% at 10+ | success binned by action count | New instrumentation | W4
Long-Horizon | State Consistency | Correct world state throughout task | >90% | WorldState vs stage per step | Unlocked by Isaac | W1
Long-Horizon | Long-Horizon Recovery | Recovery rate in multi-step tasks | >80% | recoveries filtered by horizon | New instrumentation | W4
Grouped by what unblocks each metric, which is what the schedule sequencing derives from.

## Baselines
System | Task Success | Reasoning | World Model | Safety | Recovery | Generalization | Efficiency | Weighted score | Notes
Oracle | [8 empty] | Ceiling on everything except reasoning. Not a baseline to beat — when RRM-1 trails it the gap is the reasoner, when it fails the bug is elsewhere.
Classical Robotics | [8 empty] | Scripted planner, no learned components.
LLM + Classical Planner | [8 empty] | Language to symbolic plan, classical motion.
VLM + Classical Planner | [8 empty] | Vision-language grounding, classical motion.
VLA (Baseline A) | [8 empty] | Mission plus camera straight to policy. No world model, no symbolic safety gate.
RRM without World Model (B) | [8 empty] | Reasoner and planner, stateless.
RRM without Predictive Planning (C) | [8 empty] | World model, no forward simulation of candidate actions.
RRM-1 | [8 empty] | Full stack.
Do not fill the weighted score column until the weights are validated — see Weights tab.

## Weights
Category | Weight | Status
Task Success | 25% | Hypothesis — not validated
Reasoning | 15% | Hypothesis — not validated
World Model | 15% | Hypothesis — not validated
Safety | 15% | Hypothesis — not validated
Recovery | 10% | Hypothesis — not validated
Generalization | 10% | Hypothesis — not validated
Efficiency | 10% | Hypothesis — not validated
Total
These weights are a hypothesis. A single number computed from unvalidated weights invites a reviewer to reject the framing rather than engage with the result. Report the per-metric table until there is evidence about which metrics actually co-vary.
Safety is not tradeable: any hard violation fails the run regardless of task success.
Note: docs/evaluation_matrix.md targets >85% here while docs/benchmarks.md advises no composite. Resolve before publication.